# Software Project Management (SPM)

Academic Claim Management System

YEAR 3 (A) CSSE 2026-2027

GROUP SIX(6)

ROLL NUMBER

202412203 UMUGANWA NELLY

202412898 NELSON GABRIEL

202412138 OMER ALSHAFEI

202312275 YOHANA RAMADAN

202412914 TUMUKUNDE DIVINE

202412001 HATUNGIMANA JUSTIN

202411685 NIYOKWIZERWA HERTIER

202412837 MOUAYAD ABDULAZIM

202411715 AHMED ALJAILY

202412604 AHMED YASIR AHMED

202412458 BRIAN KITARA

202412946 SAIDA HUSSEIN AHMED

## 1. Introduction to the Academic Claim Management System project

An Academic Claim Management System (ACMS) is a software application designed to manage student academic claims electronically. A claim is a formal request by a student to have an academic result reviewed or corrected, for example a missing mark, a calculation error, a wrongly recorded grade, or a request for re-marking. The system helps students, lecturers, heads of department, the examinations office, the registrar, and IT staff submit, track, review, and resolve claims efficiently.

Instead of relying on handwritten claim letters, paper forms passed between offices, and separate mark registers, the university uses an integrated system to manage the whole claim process.

### Example of the problem

Suppose a university in Rwanda has 8,000 students. After each semester, about 600 students submit claims about their results. Claims are submitted on paper and carried from office to office.

The university may experience the following problems:

- Students do not know whether their claim was received or who is handling it.

- Claim forms are lost, duplicated, or delayed between offices.

- Lecturers receive claims late and cannot easily see the original marks.

- Claims take weeks to resolve, and deadlines are missing.

- Marks corrections are not always recorded in the official results.

- The examinations office cannot easily see how many claims are pending or which courses generate the most claims.

- Management cannot obtain accurate reports on claim volumes and resolution times.

To solve these problems, the university proposes developing an Academic Claim Management System.

The SPM task is not simply to write the software. It is to plan, organize, estimate, schedule, execute, monitor, control, and deliver the software project within agreed constraints of scope, time, cost, quality, and risk.

## 2. Applying the Software Project Management framework

The SPM framework provides a structured approach to managing the ACMS project from the initial idea through implementation and maintenance.

- Project Initiation: Identify the problem, opportunity, purpose, and stakeholders.

- Feasibility Study and Business Case: Evaluate technical, economic, operational, legal, and schedule feasibility.

- Project Charter and Planning: Define objectives, scope, resources, budget, risks, and responsibilities.

- Design and Development: Design the architecture, database, interfaces, and software modules.

- Testing and Deployment: Verify quality, security, integration, and readiness for university use.

- Monitoring, Closure, and Maintenance: Track performance, obtain acceptance, train users, and maintain the system.

These phases provide an overall structure. Monitoring and control take place throughout the project, not only at the end.

## 3. Step 1: Project initiation

Project initiation establishes why the project is needed and whether it is worth investigating further.

### 3.1 Identify the problem

A problem statement describes the existing situation and the difficulties that the project should solve.

Problem statement for the ACMS: The university currently manages student claims, claim review, mark verification, and result correction through manual or disconnected processes. These processes cause long processing times, lost documents, poor communication with students, delayed corrections, and weak management reporting.

The university needs an integrated software system that improves transparency, processing speed, record accuracy, and coordination between offices.

### 3.2 Identify the opportunity

An opportunity describes an improvement that the organization could achieve. For the ACMS project, opportunities include:

- Allowing students to submit claims online and track their status.

- Routing claims automatically to the correct lecturer and department.

- Giving reviewers access to the original marks and supporting evidence.

- Sending automatic notifications and deadline reminders.

- Recording approved corrections with a full audit trail.

- Generating accurate reports to support better academic planning.

Difference: A problem explains what is wrong today; an opportunity explains what could be improved in the future.

### 3.3 Define the project purpose

The project purpose explains why the project is being undertaken.

Project purpose: To develop and implement a secure, integrated Academic Claim Management System that digitizes claim submission, review, decision, result correction, notification, and reporting to improve processing speed, transparency, record accuracy, and student satisfaction.

### 3.4 Identify the project objectives

Objectives specify the results that the project intends to achieve. They should be measurable whenever possible.

| Objective | Proposed success measure |
| --- | --- |
| Improve claim submission | Students can submit a complete claim online in under 10 minutes. |
| Improve processing speed | Reduce average claim resolution time by 50% within one semester of implementation. |
| Improve transparency | 100% of claims have a trackable status visible to the student. |
| Improve record accuracy | Record every approved mark correction with an audit trail and no unrecorded changes. |
| Improve communication | Send automatic notifications at each key stage of the claim. |
| Improve reporting | Generate agreed claim reports within two minutes under normal operating conditions. |
| Protect academic information | Enforce role-based access, audit logging, backups, and security testing before go-live. |

These are proposed targets for planning, not guaranteed outcomes. The project team must establish baseline measurements and validate the targets with university management.

## 4. Step 2: Identify stakeholders

Stakeholders are individuals or organizations that influence the project, use the system, approve its development, or are affected by its results.

| Stakeholder | Responsibilities and interests |
| --- | --- |
| University management | Approves the project, budget, and major decisions. |
| Project sponsor | Provides authority, funding support, and organizational direction. |
| Project manager | Plans activities, assigns tasks, manages risks, and monitors progress. |
| Students | Submit claims, upload evidence, track status, and receive decisions. |
| Lecturers | Review claims about their courses, verify marks, and recommend decisions. |
| Heads of department | Supervise reviews, resolve disputes, and approve recommendations. |
| Examinations office | Validates decisions and updates official results. |
| Registrar | Holds final authority over academic records and policy. |
| IT team | Develops, deploys, secures, and maintains the system. |
| Quality assurance and auditors | Verify compliance with academic regulations and data-protection requirements. |

### Example of stakeholder conflict

The registrar may want the system delivered in four months, while lecturers and heads of department may request many advanced features, such as multi-level appeals and plagiarism checks, that require additional development time.

The project manager should:

- Collect and document the requirements.

- Prioritize essential features.

- Explain the effects of additional requirements on cost and schedule.

- Agree on a realistic initial release.

- Place lower-priority features into later releases if necessary.

This is an example of stakeholder management and scope management.

## 5. Step 3: Conduct the feasibility study

A feasibility study determines whether the proposed project can reasonably be implemented.

### 5.1 Technical feasibility

Can the university obtain the required hardware, software, network infrastructure, technical expertise, and cybersecurity capabilities?

Example: The university evaluates whether its servers, campus network, and internet connectivity can support the proposed system, including access from student phones.

### 5.2 Economic feasibility

Do the expected benefits justify the total implementation and operating costs?

Example: Compare software development, equipment, training, hosting, and maintenance costs with expected savings in paper, staff time, and error correction.

### 5.3 Operational feasibility

Will students and staff be able and willing to use the system?

Example: Test proposed workflows with students, lecturers, heads of department, and examinations staff before finalizing the design.

### 5.4 Legal and regulatory feasibility

Can the system comply with applicable privacy, academic-record, and cybersecurity requirements, including Rwanda's data-protection law and the university's own regulations?

Example: Establish authorized access, confidentiality protections, audit trails, retention rules, and secure information-sharing procedures.

### 5.5 Schedule feasibility

Can the team deliver the agreed scope within the available time?

Example: Determine whether a six-month deadline is realistic for the selected modules, integration with the existing student information system, testing, and staff training.

Feasibility decision: The sponsor may approve the project, request changes to its scope or budget, commission further investigation, or reject it if the benefits and risks do not justify the investment.

## 6. Step 4: Develop the business case

The business case explains why the university should invest in the ACMS.

### Expected benefits

- Reduced paperwork and administrative duplication.

- Faster retrieval of claim information and original marks.

- Better coordination among students, lecturers, departments, and the examinations office.

- Fewer lost or delayed claims.

- More reliable correction of academic records.

- Better access to information for academic decision-making.

### Illustrative financial analysis

Assume the following hypothetical figures, expressed in Rwandan francs (RWF).

| Item | Estimated amount (RWF) |
| --- | --- |
| Initial development and implementation | 20,000,000 |
| Annual hosting, support, and maintenance | 4,000,000 |
| Expected annual financial savings | 12,000,000 |
| Annual net benefit after operating costs | 8,000,000 |

Using these assumptions:

Payback period = Initial investment ÷ Annual net benefit = 20,000,000 ÷ 8,000,000 = 2.5 years

The estimated payback period is 2.5 years, assuming the projected annual net benefit is achieved.

This calculation excludes discounting, financing costs, taxes, and other possible costs or benefits. The actual business case would require validated quotations and university-specific data.

## 7. Step 5: Prepare the Project Charter

A Project Charter formally authorizes the project and establishes its high-level direction.

Project Charter: Academic Claim Management System (illustrative project document)

| Item | Description |
| --- | --- |
| Project title | Academic Claim Management System (ACMS) Development and Implementation |
| Project sponsor | Vice-Chancellor / University Management |
| Project manager | To be appointed by the sponsor |
| Project purpose | To digitize and integrate the academic claim submission, review, decision, and result-correction workflow. |
| Main objectives | Enable online claims; route claims to reviewers; track status and deadlines; record approved corrections; strengthen security and reporting. |
| High-level scope | Student claim submission, evidence upload, routing, review, decisions, notifications, result-correction records, reporting, access control, and audit logging. |
| Major deliverables | Requirements specification, system design, tested software modules, migrated and validated data where applicable, user documentation, training, deployment, and maintenance plan. |
| Estimated duration | 6 months, subject to requirements and feasibility validation. |
| Illustrative initial budget | RWF 20,000,000 for implementation, subject to detailed estimation and approval. |
| Major risks | Unauthorized grade changes, data loss, integration failures, user resistance, inaccurate migration, and schedule delays. |
| Approval authority | Vice-Chancellor or authorized governing body |

Approval signatures: Project Sponsor ____________ Project Manager ____________ Date ____________

The charter is a high-level authorization document. Detailed requirements, task assignments, budgets, and technical specifications are developed during planning.

## 8. Step 6: Define the project scope

Scope management defines what the project will deliver and prevents uncontrolled expansion of requirements.

### 8.1 In-scope features

The initial release will include:

- User login, logout, and role-based access.

- Student claim submission with supporting evidence upload.

- Claim registration, unique claim numbers, and status tracking.

- Automatic routing of claims to the responsible lecturer and department.

- Review, recommendation, and decision workflow.

- Result-correction requests and approval by the examinations office.

- Email and SMS notifications and deadline reminders.

- Dashboards and claim reports.

- Audit logs, backup procedures, and system administration.

### 8.2 Out-of-scope features

Unless specifically approved, the initial release will not include:

- Automated marking or AI-based grading decisions.

- Plagiarism detection.

- A full student information system replacement.

- Online payment of re-marking fees.

- A national academic-records exchange.

- Integration with every external university or government system.

Some of these features may be considered in later releases.

### 8.3 Scope creep

Scope creep occurs when new features are added without formal assessment and approval of their effects on schedule, cost, quality, or resources.

Example: After development begins, management requests a mobile application, an online payment gateway, and a chatbot without changing the delivery date or budget.

The project manager should record the request, assess its impact, obtain approval through change control, and revise the project plan if the change is accepted.

## 9. Step 7: Gather and document requirements

Requirements describe what the system must do and the conditions under which it must operate.

### 9.1 Functional requirements

These describe system functions.

| ID | Requirement | Example |
| --- | --- | --- |
| FR-01 | Claim submission | A student can submit a claim for a course result with a reason and evidence. |
| FR-02 | Claim tracking | Students can view the current status and history of their claims. |
| FR-03 | Claim routing | The system assigns each claim to the correct lecturer and department. |
| FR-04 | Claim review | A lecturer can view original marks, verify them, and record a recommendation. |
| FR-05 | Decision management | A head of department can approve, reject, or escalate a recommendation. |
| FR-06 | Result correction | The examinations office can apply an approved correction with a recorded reason. |
| FR-07 | Notifications | The system notifies users of submission, assignment, decision, and deadlines. |
| FR-08 | Reporting | Management can generate reports on claim volumes, outcomes, and resolution times. |
| FR-09 | Access control | Users can access only the functions and information authorized for their roles. |
| FR-10 | Audit logging | The system records access and changes to sensitive records. |

### 9.2 Non-functional requirements

These specify quality attributes and system-wide constraints.

| Attribute | Example target |
| --- | --- |
| Performance | 95% of routine requests respond within 3 seconds under an agreed test load. |
| Availability | Target 99.5% availability per month, with higher availability during claim periods. |
| Security | Strong authentication, role-based permissions, encryption, and audit logging. |
| Scalability | Support peak claim periods after results are released, with capacity testing. |
| Usability | Provide clear interfaces usable on phones and computers, with task-based training. |
| Reliability | Use monitored services, validated backups, and tested recovery procedures. |
| Maintainability | Use documented modules, version control, and automated tests. |
| Data integrity | Enforce validation, unique identifiers, and consistent transaction handling. |
| Privacy | Collect and disclose student information only for authorized purposes. |

The targets are examples for discussion and must be approved after the university's needs, infrastructure, and risks have been assessed.

### 9.3 Example user story

As a student, I want to submit a claim about a mark and upload my evidence so that the responsible lecturer can review it and I can track the outcome.

Acceptance criteria:

- Required fields (course, assessment, reason) are validated before saving.

- The student can attach supporting files within the allowed size and type.

- A successful submission produces a unique claim number.

- The system confirms submission and notifies the assigned reviewer.

- The claim cannot be submitted after the official claim deadline unless an authorized user approves it.

Acceptance criteria make requirements testable.

## 10. Step 8: Develop the Work Breakdown Structure (WBS)

A Work Breakdown Structure (WBS) divides the project into manageable deliverables and work packages. It helps the project manager estimate costs, assign responsibilities, and track progress.

ACMS Project
+-- 1. Project Management
|   +-- 1.1 Project charter and plan
|   +-- 1.2 Monitoring and reporting
|   +-- 1.3 Risk and change management
|
+-- 2. Requirements
|   +-- 2.1 Stakeholder interviews
|   +-- 2.2 Requirements specification
|   +-- 2.3 Requirements approval
|
+-- 3. Design
|   +-- 3.1 System architecture
|   +-- 3.2 Database design
|   +-- 3.3 User interface design
|
+-- 4. Development
|   +-- 4.1 Authentication and access control module
|   +-- 4.2 Claim submission module
|   +-- 4.3 Review and workflow module
|   +-- 4.4 Result correction module
|   +-- 4.5 Notification module
|   +-- 4.6 Reporting module
|
+-- 5. Testing
|   +-- 5.1 Unit testing
|   +-- 5.2 Integration testing
|   +-- 5.3 Security and performance testing
|   +-- 5.4 User acceptance testing
|
+-- 6. Deployment and Training
|   +-- 6.1 Infrastructure configuration
|   +-- 6.2 Data migration and validation
|   +-- 6.3 Staff and student training
|   +-- 6.4 Production deployment
|
+-- 7. Project Closure
    +-- 7.1 Final acceptance
    +-- 7.2 Documentation and handover
    +-- 7.3 Lessons learned

### Example of a WBS work package

Consider work package 4.3: Review and workflow module. Its tasks may include:

- Design the claim status model (submitted, assigned, under review, decided, closed).

- Develop routing rules by course and department.

- Implement lecturer review and recommendation screens.

- Implement head-of-department approval and escalation.

- Add deadline tracking and overdue alerts.

- Test workflow transitions and permissions.

- Obtain acceptance from lecturers and examinations office representatives.

The work package is complete when its defined deliverables pass the agreed acceptance criteria.

Important distinction: A WBS describes what work must be delivered. A schedule describes when the work will be performed.

## 11. Step 9: Plan project resources and organization

### 11.1 Proposed project team

| Role | Main responsibility |
| --- | --- |
| Project sponsor | Authorizes funding and major decisions. |
| Project manager | Coordinates scope, schedule, budget, resources, and risks. |
| Business analyst | Collects requirements and documents claim workflows. |
| Software architect | Designs system structure and technical standards. |
| UI/UX designer | Designs usable interfaces for students and staff. |
| Backend developers | Implement business logic, APIs, and database operations. |
| Frontend developers | Develop the user interface. |
| Database administrator | Designs, secures, backs up, and maintains the database. |
| QA engineers | Test functionality, integration, security, and performance. |
| Cybersecurity specialist | Assesses threats, access controls, and security weaknesses. |
| DevOps/system administrator | Manages deployment, infrastructure, monitoring, and recovery. |
| Academic representatives | Validate claim workflows and academic-regulation requirements. |
| Trainer/support staff | Prepare users, deliver training, and support adoption. |

Some roles may be combined in a small project, but academic validation, independent testing, and security review should remain clearly assigned.

### 11.2 Responsibility assignment matrix (RACI)

RACI means:

- R, Responsible: Performs the work.

- A, Accountable: Owns the result and approves it.

- C, Consulted: Provides input.

- I, Informed: Receives updates.

| Activity | Project manager | University sponsor | Development team | Academic representatives |
| --- | --- | --- | --- | --- |
| Approve project charter | R | A | I | C |
| Gather requirements | A | I | R | R |
| Approve claim workflows | C | I | C | A/R |
| Develop software | A | I | R | C |
| Test claim workflows | C | I | R | A/R |
| Approve go-live | R | A | C | C |

A detailed RACI matrix should be checked to ensure each activity has a clear accountable owner.

## 12. Step 10: Estimate project cost and effort

Software estimation predicts the effort, duration, resources, and money required to deliver the project.

### 12.1 Estimation methods

- Expert judgment: Experienced project managers and developers estimate work.

- Analogous estimation: Use the actual cost and duration of similar completed projects.

- Parametric estimation: Apply a cost or effort rate to a measurable quantity.

- Bottom-up estimation: Estimate each WBS work package and add the results.

- Three-point estimation: Estimate optimistic, most likely, and pessimistic effort.

For three-point estimation using the PERT weighted average:

E = (O + 4M + P) ÷ 6

Suppose development of the review and workflow module is estimated at 10 person-days optimistically, 15 person-days most likely, and 26 person-days pessimistically.

E = (10 + 4(15) + 26) ÷ 6 = 96 ÷ 6 = 16

The estimated effort is 16 person-days.

Person-days measure effort, not calendar duration. A 16-person-day task does not necessarily take 16 calendar days if multiple people work on it or if dependencies constrain progress.

### 12.2 Illustrative project budget

The following is an example of how the implementation budget might be organized. These are hypothetical planning figures, not a market quotation.

| Cost item | Estimated cost (RWF) |
| --- | --- |
| Requirements and project planning | 2,000,000 |
| System and database design | 2,000,000 |
| Software development | 7,000,000 |
| Testing and security assessment | 2,000,000 |
| Infrastructure and deployment | 2,000,000 |
| Data migration and validation | 1,000,000 |
| Staff training and documentation | 1,500,000 |
| Project management and coordination | 1,500,000 |
| Subtotal | 19,000,000 |
| Contingency reserve (approximately 5.26% of subtotal) | 1,000,000 |
| Total project budget | 20,000,000 |

## 13. Step 11: Build the project schedule

A project schedule defines tasks, durations, dependencies, milestones, and the expected completion date.

The following is an illustrative six-month schedule. Tasks within some phases can overlap when their dependencies permit.

| Phase | Activity | Duration | Planned period |
| --- | --- | --- | --- |
| 1 | Initiation and charter approval | 2 weeks | Month 1 |
| 2 | Requirements gathering and approval | 3 weeks | Months 1–2 |
| 3 | Architecture and database design | 3 weeks | Month 2 |
| 4 | Core software development | 8 weeks | Months 2–4 |
| 5 | Integration and additional module development | 4 weeks | Months 4–5 |
| 6 | System, security, and user acceptance testing | 3 weeks | Month 5 |
| 7 | Data migration, training, and deployment | 3 weeks | Months 5–6 |
| 8 | Handover and formal closure | 2 weeks | Month 6 |

The dates and durations require validation through task-level estimates and dependency analysis. The phases overlap, so their durations must not simply be added to calculate the total project duration.

Key milestones: charter approved (end of Month 1); requirements signed off (Month 2); core system complete (Month 4); user acceptance passed (Month 5); go-live (Month 6).

## 14. Step 12: Manage project risks

Risk management identifies uncertain events that could affect the project and plans how to respond. A common method scores each risk by Risk score = Probability × Impact, using a 1 to 5 scale for each.

| Risk | Probability (1–5) | Impact (1–5) | Score | Response |
| --- | --- | --- | --- | --- |
| Unauthorized changes to student marks | 2 | 5 | 10 | Role-based access, approval workflow, audit logs, security testing. |
| Data loss or corruption during migration | 3 | 5 | 15 | Backups, trial migrations, validation checks, rollback plan. |
| Integration with existing results system fails | 3 | 4 | 12 | Early integration prototype, agreed data formats, fallback manual import. |
| User resistance from staff | 4 | 3 | 12 | Early involvement, training, visible sponsor support. |
| Requirements change repeatedly | 4 | 3 | 12 | Change control, prioritized releases, signed-off requirements. |
| System overload when results are released | 3 | 4 | 12 | Load testing, scalable hosting, monitoring. |
| Key team member leaves | 2 | 4 | 8 | Documentation, knowledge sharing, backup assignments. |
| Schedule delays | 4 | 3 | 12 | Buffers, weekly tracking, early escalation of problems. |

Common response strategies are avoid (remove the cause), mitigate (reduce probability or impact), transfer (shift to a third party, such as a hosting provider), and accept (monitor and keep a contingency reserve). Risks are reviewed regularly, not only once.

## 15. Step 13: Monitor and control the project

Monitoring compares actual progress with the plan; control takes corrective action when they differ.

### 15.1 Monitoring tools

- Weekly status meetings and progress reports.

- Task boards and burn-down charts.

- Milestone reviews with the sponsor.

- Risk register reviews.

- Defect tracking and test reports.

- Change request log.

### 15.2 Earned Value Management example

Assume the total budget (BAC) is RWF 20,000,000. At the end of Month 3, the plan said 40% of the work should be done, but only 35% is complete, and RWF 7,500,000 has been spent.

| Measure | Formula | Result |
| --- | --- | --- |
| Planned Value (PV) | 40% × 20,000,000 | 8,000,000 |
| Earned Value (EV) | 35% × 20,000,000 | 7,000,000 |
| Actual Cost (AC) | Given | 7,500,000 |
| Cost Variance (CV) | EV − AC | −500,000 |
| Schedule Variance (SV) | EV − PV | −1,000,000 |
| Cost Performance Index (CPI) | EV ÷ AC | 0.93 |
| Schedule Performance Index (SPI) | EV ÷ PV | 0.875 |
| Estimate at Completion (EAC) | BAC ÷ CPI | about 21,430,000 |

Interpretation: CPI and SPI are below 1, so the project is over budget and behind schedule. If the trend continues, the project will finish at about RWF 21.4 million, exceeding the budget by roughly RWF 1.4 million. The project manager should investigate the causes, consider reducing lower-priority scope, adding resources where tasks can be shortened, and report the situation to the sponsor.

### 15.3 Change control

Every change request should be recorded, assessed for its effect on scope, cost, schedule, quality, and risk, approved or rejected by the authorized body, and reflected in the updated plan.

## 16. Project closure and maintenance

Closure formally ends the project. It includes final acceptance by the sponsor, handover of source code, documentation, and administrator guides, final training, release of resources, and a lessons-learned review that records what went well, what went wrong, and what to improve in future projects.

After go-live, the system enters maintenance:

- Corrective: fix defects.

- Adaptive: adjust to changes in regulations or the university's systems.

- Perfective: add improvements such as those placed in later releases.

- Preventive: improve security, performance, and code quality.